## Cover Page
Tourism Management System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Abhisek Das
| Role | Intern
Signature
| Date | 2022-06-17
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Tourism Management System Project ID: A062 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priorities | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Admin Registration/Authentication | Admin | As Admin I want the system to procure the fundamental details of the admin | 1- Admin details should be pre loaded in the system 2- Login and Authentication should be handled and appropriate error message when wrong passwords are typed. | Critical
US_2 | User Registration | User | As User I want the system to procure the fundamental details of the use | 1-When the User clicks on User Registration link, it should re-direct to User registration form 2-User needs to fill some of the basic attributes/fields as mentioned below in the requirement: First Name-3 -15 Character Last Name-3-15 Character Contact Number- 10 digit, numeric Email-Presence of @ should be checked Password- MInimum 6 in length, with special charaters and numerics. DOB - drop down calendar, Age >18 Note - Trainees can add the fields as required 4-Clicking ‘Submit’ should validate the datatype constraints for each field 5-Users failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | Critical
US_3 | User Authentication | User | As User I want the system to authenticate the User credentials of the registered User | 1-A registered User – is able click ‘User Login’ link, after keying in ‘Email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical
US_4 | Manager Registration | Manager | As Manager I want the system to procure the fundamental details of the use | 1-When the Manager clicks on Manager Registration link, it should re-direct to Manager registration form 2-Manager needs to fill some of the basic attributes/fields as mentioned below in the requirement: First Name, Last Name, Contact Number, Email, Password Note - Use validations as in US_2 3-Manager needs to select his Skills from available checkboxes 4-Clicking ‘Submit’ should validate the datatype constraints for each field 5-Managers failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. Note - Use Drop downs, radio buttons and check boxes wherever possible | Critical
US_5 | Manager Authentication | Manager | As Manager I want the system to authenticate the Manager credentials of the registered Manager | 1-A registered Manager – is able click ‘Manager Login’ link, after keying in ‘Email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical
US_6 | Create Package | Admin | As Admin I want to create tour package | 1-Admin should be able create various type of tour packages for eg - 3N-4Days, One day Picnic Package, Honeymoon package etc | Critical
US_7 | Manage Package | Admin | As Admin, I want to manage the packages | 1-Admin should be able to edit/Delete the packages. Note - Use Pagenation to list the package. | Critical
US_8 | Select package | Users | As Users, I want to select tour packages | 1-Users on login should land in the home page. 2-Home page should be displaying various packages available for the users to select 3-User should be able to search based on location, number of days etc 4- Search result should be displayed and User should be able to select the package they like | Critical
US_9 | Confirm Booking | Users | As Users, I want to pay for the tour and confirm booking | 1-User on selecting the package, should be directed to get the user details 2- This should include - Number of persons, No of rooms required, Mode of transport, Date of travel etc. 3-On getting details, user should be able pay for the tour | Critical
US_10 | Payment | Users | As Users, I want to pay for the tour and confirm booking | 1-User should be displayed with different options of payment method 2-Appropriate message should be displayed on successful/failed transaction. 3-Payment should be mocked | Critical
US_11 | Manage Inquires | Manager | As Manager, I want to manage inquiries | 1-User should be able to post inquires about the tour package details 2-Manager should be able to view and post the replies for the queries posted by the user | Medium
US_12 | Raise Complaints | Users | As User, I want to raise complaints | 1- User should be able to raise complaints in case of any issues. 2-Complaints should be raised only by the user who has booked and travelled. 3-Complaint number should be auto generated | Medium
US_13 | Manage issues | Manager | As Manager, I want to manage the issues | 1-Manager should be able to view the complaints raised by the users and resolve it. 2- The status of the issue should be update and notified to the user who raised the complaint. | Medium
US_14 | Create Feedback | Manager | As Manager, I want to create feedback form for the users | 1- Manager should be able to create feedback forms with different queries. | Low
US_15 | User Feedback | Users | As Users, I want to give feedback | 1-User should be notified to fill the feedback form after the return from their tour 2- Users should be able to provide the feedback for the queries created by the manager | Low
US_16 | Feedback report | Manager | As Manager, I want to generate the feedback report | 1-Manager should be able to generate the feedback report. 2- Manager should select the start date and the end date 3-All the feedback submitted by the users during the selected period should be listed and should be in downloadable excel format. | Low
US_17 | Admin report | Admin | As Admin, I should be able to generate booking report | 1-Admin should be able to generate the tour booking report. 2- Admin should select the start date and the end date 3-All thetour bookings during the selected period should be listed and should be in downloadable excel format. | Low
US_18 | Log off | All Users | All the users want to log off | 1- All user should be able to log off from the application | Critical

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000