## Cover Page
Tourism Management System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Abhisek Das
| Role | Intern
Signature
| Date | 2022-06-17
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint -1
Sprint Backlog Tourism Management System Project ID: INTCDB22DX012 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Admin Details | 8
Task_1 | Loading all admin details on the page |  | Ambuj Tiwari | Completed | 1
Task_2 | Creating Authentication handler class to show appropriate error messages for wrong input |  | Ambuj Tiwari | Completed | 1
User Story #2 | User Registration | 8
Task_1 | Redirecting to the registration page by clicking the link |  | Arkajyoti Saha | Completed | 2
Task_2 | Creating the form for users to enter their credentials |  | Arkajyoti Saha | Completed | 2.8
Task_3 | Validation logic upon clicking the Submit button |  | Arkajyoti Saha | Completed | 0.4
Task_4 | Showing alert message for users failing to enter mandatory fields |  | Arkajyoti Saha | Completed | 0.2
Task_5 | Upon validation, saving the data in the database |  | Arkajyoti Saha | Completed | 7
User Story #3 | User Authentication | 8
Task_1 | Creating user login link where user enters credentials |  | Anamitra Das | Completed | 0.8
Task_2 | Validating the user's information from the database |  | Anamitra Das | Completed | 2.3
User Story #4 | Manager Registration | 8
Task_1 | Creating Manager Registration page |  | Ambuj Tiwari | Completed | 2.2
Task_2 | Validating the manager's details according to the given constraints |  | Ambuj Tiwari | Completed | 0.4
Task_3 | Storing the manager's details into the database |  | Abhisek Das | Completed | 0.2
User Story #5 | Manager Authentication | 8
Task_1 | Creating manager login page UI |  | Ambuj Tiwari | Completed | 1.3
Task_2 | Authenticating the manager id and password with the database and directing to manager homepage |  | Arkajyoti Saha | Completed | 0.2
TOTAL |  |  |  |  | 21.8 | 0 | 0 | 0 | 0 | 0

## Sprint -2
Sprint Backlog Tourism Management System Project ID: INTCDB22DX012 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #6 | Creating Tour Packages | 8
Task_1 | Admin homepage where admin can add different packages to database |  | Ambuj Tiwari | Completed | 2.6
Task_2 | Storing the package details in database |  | Abhisek Das | Completed | 0.5
User Story #7 | Managing Tour Packages | 8
Task_1 | Admin homepage where an option to edit package is present |  | Abhisek Das | Completed | 0.1
Task_2 | UI for admin to modify the package details |  | Ambuj Tiwari | Completed | 2.3
Task_3 | Saving the modifications into the database |  | Abhisek Das | Completed | 0.3
User Story #8 | User Package Selection | 8
Task_1 | User homepage button to go to tour packages |  | Abhisek Das | Completed | 0.1
Task_2 | Displaying all the tour packages from the database to the user |  | Abhisek Das | Completed | 1.4
Task_3 | Users searching the packages based on price, location etc. |  | Arkajyoti Saha | Completed | 1.3
Task_4 | Search results displayed in the user page |  | Arkajyoti Saha | Completed | 0.1
User Story #9 | Booking Confirmation | 8
Task_1 | Users directed to booking form on selecting the package |  | Abhisek Das | Completed | 0.2
Task_2 | UI to store user's details and choices |  | Abhisek Das | Completed | 2.3
Task_3 | On submitting, users should be directed to payment options |  | Abhisek Das | Completed | 0.9
User Story #10 | Payment | 8
Task_1 | Users are shown number of payment options |  | Abhisek Das | Completed | 1.1
Task_2 | On selecting an option user is directed to payment page |  | Abhisek Das | Completed | 0.3
Task_3 | The payment is mocked |  | Arkajyoti Saha | Completed | 2
Task_4 | Payment bill is generated after successful transaction |  | Arkajyoti Saha | Completed | 0.2
TOTAL |  |  |  |  | 15.7 | 0 | 0 | 0 | 0 | 0

## Sprint -3
Sprint Backlog Tourism Management System Project ID: INTCDB22DX012 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #11 | Managing Inquiries | 8
Task_1 | Creating an option in user homepage to post inquiries |  | Anamitra Das | Completed | 0.3
Task_2 | Storing the user inquiries in database |  | Ananya Samanta | Completed | 0.2
Task_3 | Creating an option in manager homepage to display the queries |  | Anamitra Das | Completed | 0.1
Task_4 | Creating form corresponding to all user queries where manager can post replies |  | Ananya Samanta | Completed | 2.3
User Story #12 | User Complaints | 8
Task_1 | Creating an option in user homepage to post complaints |  | Abhisek Das | Completed | 0.1
Task_2 | Authenticating users to complaint page who have purchased a package |  | Ananya Samanta | Completed | 0.6
Task_3 | Storing user complaints in the database |  | Anamitra Das | Completed | 0.3
Task_4 | Complaint number is auto-generated |  | Ananya Samanta | Completed | 1.1
User Story #13 | Managing User Complaints | 8
Task_1 | Creating option in the manager homepage to view the user complaints |  | Abhisek Das | Completed | 0.3
Task_2 | The complaints should be marked green after it is resolved by the manager |  | Anamitra Das | Completed | 2.3
User Story #14 | Creating Feedback Form | 8
Task_1 | Creating option in the manager homepage to create feedback forms for users to fill |  | Abhisek Das | Completed | 0.2
Task_2 | UI for manager to add the required headings for the form |  | Abhisek Das | Completed | 1.9
Task_3 | Storing the points in database and adding to the feedback form of the user |  | Abhisek Das | Completed | 0.5
User Story #15 | User Feedback Form | 8
Task_1 | Creating option in the user homepage to fill the feedback form |  | Abhisek Das | Completed | 0.2
Task_2 | The feedback form is submitted by the user and is stored in the database |  | Abhisek Das | Completed | 1.2
Task_3 | Creating a log out button in the user homepage for users to log off the application |  | Ananya Samanta | Completed | 0.5
TOTAL |  |  |  |  | 12.1 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A